# Product Backlog – BCLC Consulting Project – S03 Red Triangle

Project Goal: Assess BCLC’s online Sportsbook presence and develop innovative product offerings & marketing strategies

Product Owner: Emmanuel Morris-Odubo

| ID | Task | Dependency | Category |
| --- | --- | --- | --- |
| P1 | Analyze PlayNow sportsbook footprint | N/A | Current Footprint |
| P2 | Assess website traffic sources | N/A | Current Footprint |
| P3 | Evaluate user behavior metrics | N/A | Current Footprint |
| P4 | Analyze app performance issues | N/A | Current Footprint |
| P5 | Review user engagement metrics | N/A | Current Footprint |
| C1 | Identify top 5 competitors | N/A | Competitive Analysis |
| C2 | Analyze BC market share | C1 | Competitive Analysis |
| C3 | Compare PlayNow vs competitors | C1 | Competitive Analysis |
| C4 | Benchmark competitor best practices | C2 | Competitive Analysis |
| C5 | Review competitor loyalty programs | C4 | Competitive Analysis |
| M1 | Research sportsbook marketing trends | N/A | Marketing Strategy & Product Innovation |
| M2 | Audit PlayNow marketing strategy | P5 | Marketing Strategy & Product Innovation |
| M3 | Develop 3 marketing campaigns | P2 | Marketing Strategy & Product Innovation |
| M4 | Identify new acquisition strategies | P2 | Marketing Strategy & Product Innovation |
| PX1 | Research sportsbook product innovations | M1 | Marketing Strategy & Product Innovation |
| PX2 | Develop product differentiation strategy | C' | Marketing Strategy & Product Innovation |
| PX3 | Explore gamification opportunities | PX2 | Marketing Strategy & Product Innovation |
| PX4 | Enhance AI personalization strategies | PX3 | Marketing Strategy & Product Innovation |
| I1 | Create marketing rollout plan | PX' | Implementation |
| I2 | Define resource allocation needs | PX' | Implementation |
| I3 | Assess legal and compliance risks | M' | Implementation |
| I4 | Develop player retention KPIs | M' | Implementation |
| I5 | Plan risk mitigation strategies | M' | Implementation |