# Sprint 1 Review & Retrospective – BCLC Consulting Project – S03 Red Triangle

## Sprint Review

### What Went Well

1. Holistic Understanding of BCLC & PlayNow

- Successfully gathered a broad overview of PlayNow’s positioning, market landscape, and competitors.

2. Multiple Deliverables Completed

- Generated three comprehensive documents covering PlayNow’s footprint, competitor analysis, and market strategies.

3. Diverse Research & Collaboration

- Each team member contributed research from multiple sources, allowing for a well-rounded perspective.

4. Identification of Research Gaps

- Key areas where more depth is required were identified, particularly in competitive analysis and quantitative market data.

5. Role Specialization Moving Forward

- Instead of all team members working on the same tasks, we now have a clearer plan to assign specific research areas.

### Gaps & Challenges in Sprint 1

1. Lack of a Defined Product Backlog at the Start

- We did not begin with a structured backlog, leading to a lack of clear dependencies and prioritization.

2. Broad Approach, Less Depth

- Since each member attempted to conduct a full analysis independently, we lacked depth in certain areas.

3. Limited Competitor Coverage

- We only analyzed two competitors (Bet365 & DraftKings) instead of five.

4. Minimal Quantitative Analysis

- Research lacked numerical insights such as market share, sportsbook offerings, and comparative feature evaluations.

5. Disjointed Scrum Process

- Backlog, sprint backlog, and team agreement were developed after the Potentially Shippable Product (PSP), reversing the intended Agile workflow.

6. Multiple Deliverables Instead of One

- Findings were split across three separate documents instead of a single comprehensive report.

7. Lack of Explicit Scrum Roles

- No explicitly defined Product Owner or Scrum Master, leading to a lack of structured task assignments and oversight.

## Adjustments for Sprint 2

### Expanded Competitive Analysis

• Identify three additional competitors in BC: Bulldog, Betway, and another BC-based sportsbook.

• Conduct in-depth quantitative research on market share, market size, sportsbook offerings, features, pricing, and promotions.

• Perform a comparative analysis evaluating PlayNow’s position against all competitors collectively.

### Enhanced PlayNow Footprint Analysis

• Research player acquisition sources, advertising spend, and promotional strategies.

• Assess PlayNow’s partnerships and its impact on BC’s sports betting market.

### Revised Product Backlog & Sprint Structure

• Redesign the Product Backlog to ensure it includes all aspects of research, analysis, and presentation.

• Integrate both technical and communication aspects such as report writing, visual presentation, and executive summaries.

• Ensure one consolidated deliverable at the end of Sprint 2.

### Task Specialization for Sprint 2

• Assign specific research roles to each team member:

- Current Footprint Analysis → One member refines PlayNow’s positioning with new findings.

- Comparative Analysis → One member focuses on evaluating competitors and PlayNow’s competitive position.

- Marketing Strategy → Two members expand on market trends, best practices, and industry innovations.

### Maintaining a Holistic Approach While Deepening Research

• Continue using a broad approach while ensuring each component is researched in depth.

• Maintain focus on competitive analysis, market strategy, and PlayNow’s current footprint.

• Implementation planning and final marketing refinements will be pushed to Sprint 3.

## Key Takeaways & Next Steps

• We gained a strong initial understanding of PlayNow’s position, competitors, and strategic opportunities.

• Our biggest gap was in depth—Sprint 2 will prioritize expanding competitor analysis, enhancing quantitative research, and refining PlayNow’s footprint evaluation.

• We need a structured backlog from the start to ensure efficiency in future sprints.

• Each team member will specialize in one area to ensure deeper, focused research.

• Sprint 2 deliverable will be consolidated into one comprehensive report.