Product Owner: Sarah

BCLC PlayNow Sports Report Outline / Product Backlog – z

1. Progress & Highlights

#### 1. Streamlined Coordination and Role Clarity

- Teams operated with strong individual ownership under Sharah’s facilitation, improving task tracking and inter-team updates.

- Red Triangle finalized key components of the Competitive Analysis, narrowing the focus to the top 3 platforms for more strategic benchmarking.

#### 2. Communication & Timelines

- All internal milestones were met as planned. Regular touchpoints kept everyone on the same page.

- Garima ensured alignment between the product backlog and the deliverables expected in the final report.

#### 3. Strategic Use of Tools

- Continued collaboration through Microsoft Teams and shared folders enabled effective file access and updates.

- AI tools supported academic sourcing and insight generation, particularly for responsible gambling research and market trends.

#### 4. Final Report Development Aligned with Product Backlog

- Significant progress made across the PlayNow Sports Report Outline:

- → Current Footprint: Completed sections on Reach and Performance; Engagement data partially populated with segmentation insights.
 → Competitive Analysis: Focused benchmarking completed for Bet365, DraftKings, and FanDuel; promotional strategies and UX evaluations captured.
 → Product Innovation: Drafted layered roadmap with feature parity and differentiated innovation (e.g., BC team integrations, gamification).
 → Marketing Strategy: Brand positioning, digital touchpoints, and cultural resonance strategy developed; community-centric tactics aligned.
 → Implementation Plan: Phased rollout structure established with metrics, timelines, and ownership lines.

#### 5. Preparing for Final Submission & Presentation

- Structure for both written report and final presentation was aligned with the backlog.

- Visual assets and supporting data for slides are in progress. Focus will now shift to slide polish and storytelling cohesion.

### Gaps & Challenges

#### 1. Limited Experiential Research

- Due to BCID restrictions, experiential testing of PlayNow was not possible. This limits firsthand UX mapping.

- Alternatives (e.g., observational studies, user reviews) partially substituted these gaps.

#### 2. Data Limitations

- Several key metrics (e.g., engagement bounce rates, exact acquisition funnels) are not publicly accessible.

- Secondary data and industry benchmarks were used to fill critical gaps.

#### 3. Final Touches Needed

- Some sections (e.g., visual layouts, product innovation justifications) need stronger data backing or visuals.

- Tone and voice need one final review for client-readiness and professionalism.

### Focus for Final Week

- Complete and polish the written report by Monday evening for internal QA.

- Finalize visual slides for key recommendations in strategy, innovation, and implementation.

- Practice and rehearse the presentation, aligning speaker flow and timing.

- Ensure all citations, figures, and visual assets are consistent, referenced, and professionally formatted.