## Scrum Backlog
Team: |  | BCLC Green Triangle Consulting | Sprint Goal: To develop a wholistic view of project and get a feel of the project scope. To identify the appropriate distribution of effort and focus for specific areas.
Team Members: |  | Digvijay Kulshreshtha
Feliz Chibuzo Obi
Manuel Chong
Roshnee Jayakumar
Scrum Master: |  | Roshnee Jayakumar
SCRUM BACKLOG REPORT
ID | CATEGORY | ASSIGNED TO | TASK | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
P1 | Footprint Analysis | All Members | Analyze PlayNow sportsbook footprint | Medium | 1 | In Progress | Not Started | High
P2 | Footprint Analysis | All Members | Assess website traffic sources | Medium | 1 | In Progress | In Progress | Medium
C1 | Competitor Analysis | All Members | Identify top 5 competitors | Medium | 1 | In Progress | Complete | Low
C2 | Competitor Analysis | All Members | Analyze BC market share | Medium | 1 | In Progress | Overdue
C3 | Competitor Analysis | All Members | Compare PlayNow vs competitors | Medium | 1 | In Progress | On Hold
M1 | Marketing Strategy & Product Innovation | All Members | Research sportsbook marketing trends | Medium | 1 | In Progress
PX1 | Marketing Strategy & Product Innovation | All Members | Research sportsbook product innovations | Medium | 1 | In Progress
I1 | Implementation Plan | All Members | Create marketing rollout plan | Medium | 1 | In Progress