## Product Backlog
Team: |  | BCLC Green Triangle Consulting | Project Goal: Assess BCLC's online Sportsbook presence and develop innovative product offerings & marketing strategies
Team Members: |  | Digvijay Kulshreshtha
Feliz Chibuzo Obi
Manuel Chong
Roshnee Jayakumar
PRODUCT BACKLOG REPORT
Sprint 1 Product Owner: |  | Manuel Chong
ID | CATEGORY | ASSIGNED TO | TASK | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
P01 | Footprint Analysis | Manuel Chong | Analyze PlayNow sportsbook footprint | Medium | 1 | Complete | Not Started | High
P02 | Footprint Analysis | Manuel Chong | Assess website traffic sources | Medium | 1 | Complete | In Progress | Medium
P03 | Footprint Analysis | Manuel Chong | Evaluate user behavior metrics | Medium | 1 | Complete | Complete | Low
P04 | Footprint Analysis | Manuel Chong | Analyze app performance issues | Medium | 1 | Complete | Overdue
P05 | Footprint Analysis | Manuel Chong | Review user engagement metrics | Medium | 1 | Complete | On Hold
C01 | Competitor Analysis | Roshnee Jayakumar | Identify top 2 competitors | Medium | 1 | Complete
C02 | Competitor Analysis | Roshnee Jayakumar | Analyze BC market share | Medium | 1 | Complete
C03 | Competitor Analysis | Roshnee Jayakumar | Compare PlayNow vs competitors | Medium | 1 | Complete
C04 | Competitor Analysis | Roshnee Jayakumar | Benchmark competitor best practices | Medium | 1 | Complete
C05 | Competitor Analysis | Roshnee Jayakumar | Review competitor loyalty programs | Medium | 1 | Complete
C06 | Competitor Analysis | Roshnee Jayakumar | Present analysis and findings in written report | Medium | 1 | Complete
M01 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Research sportsbook marketing trends | Medium | 1 | Complete
M02 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Audit PlayNow marketing strategy | Medium | 1 | Complete
M03 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Develop 3 marketing campaigns | Medium | 1 | Complete
M04 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Identify new acquisition strategies | Medium | 1 | Complete
PX05 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Research sportsbook product innovations | Medium | 1 | Complete
PX06 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Develop product differentiation strategy | Medium | 1 | Complete
PX07 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Explore gamification opportunities | Medium | 1 | Complete
PX08 | Marketing Strategy & Product Innovation | Feliz Chibuzo Obi | Enhance AI personalization strategies | Medium | 1 | Complete
I01 | Implementation Plan | Digvijay Kulshreshtha | Create marketing rollout plan | Medium | 1 | Complete
I02 | Implementation Plan | Digvijay Kulshreshtha | Define resource allocation needs | Medium | 1 | Complete
I03 | Implementation Plan | Digvijay Kulshreshtha | Assess legal and compliance risks | Medium | 1 | Complete
I04 | Implementation Plan | Digvijay Kulshreshtha | Develop player retention KPIs | Medium | 1 | Complete
I05 | Implementation Plan | Digvijay Kulshreshtha | Plan risk mitigation strategies | Medium | 1 | Complete
Sprint 2 Product Owner: |  | Roshnee Jayakumar
P01 | Footprint Analysis | Manuel Chong | Analyze PlayNow sportsbook footprint | High | 2 | Complete
P02 | Footprint Analysis | Roshnee Jayakumar | Assess website traffic sources | High | 2 | Complete
P03 | Footprint Analysis | Digvijay Kulshreshtha | Evaluate user behavior metrics | High | 2 | Complete
P04 | Footprint Analysis | Manuel Chong | Analyze app performance issues | High | 2 | Complete
P05 | Footprint Analysis | Roshnee Jayakumar | Review user engagement metrics | High