## Scrum Backlog
Team: |  | BCLC Green Triangle Consulting | Sprint Goal: To develop a wholistic view of project and get a feel of the project scope. To identify the appropriate distribution of effort and focus for specific areas.
Team Members: |  | Digvijay Kulshreshtha
Feliz Chibuzo Obi
Manuel Chong
Roshnee Jayakumar
SCRUM BACKLOG REPORT
Sprint 1 Scrum Master: |  | Roshnee Jayakumar
ID | CATEGORY | ASSIGNED TO | TASK | PRIORITY | SPRINT | STATUS | STATUS | PRIORITY
P1 | Footprint Analysis | All Members | Analyze PlayNow sportsbook footprint | Medium | 1 | Complete | Not Started | High
P2 | Footprint Analysis | All Members | Assess website traffic sources | Medium | 1 | Complete | In Progress | Medium
C1 | Competitor Analysis | All Members | Identify top 5 competitors | Medium | 1 | Complete | Complete | Low
C2 | Competitor Analysis | All Members | Analyze BC market share | Medium | 1 | Complete | Overdue
C3 | Competitor Analysis | All Members | Compare PlayNow vs competitors | Medium | 1 | Complete | On Hold
M1 | Marketing Strategy & Product Innovation | All Members | Research sportsbook marketing trends | Medium | 1 | Complete
PX1 | Marketing Strategy & Product Innovation | All Members | Research sportsbook product innovations | Medium | 1 | Complete
I1 | Implementation Plan | All Members | Create marketing rollout plan | Medium | 1 | Complete
Sprint 2 Scrum Master: |  | Manuel Chong
P01 | Footprint Analysis | Manuel Chong | Analyze PlayNow sportsbook footprint | High | 2 | Complete
P02 | Footprint Analysis | Roshnee Jayakumar | Assess website traffic sources | High | 2 | Complete
P03 | Footprint Analysis | Digvijay Kulshreshtha | Evaluate user behavior metrics | High | 2 | Complete
P04 | Footprint Analysis | Manuel Chong | Analyze app performance issues | High | 2 | Complete
P05 | Footprint Analysis | Roshnee Jayakumar | Review user engagement metrics | High | 2 | Complete
Sprint 3 Scrum Master: |  | Roshnee Jayakumar
P06 | Footprint Analysis | Roshnee Jayakumar | Compare PlayNow's traffic growth to competitors | High | 3 | Complete
P07 | Footprint Analysis | Roshnee Jayakumar | Compare PlayNow's user engagement rates to competitors | High | 3 | Complete
P08 | Footprint Analysis | Roshnee Jayakumar | Examine PlayNow declining growth post-COVID | High | 3 | Complete